## BlankTemplate
Primary Goal
Input your primary goal based on your vision here. Be descriptive if needed. Embed photos into the cell if needed.
Time | Resources | Actions | Communication | Knowledge
TRACK your primary goal here.
Critical Goals |  |  |  |  | Sub-Goal Links | Critical Goals are the non-negotiable goals. These are the goals you must accomplish to achieve success.
Time | Resources | Actions | Communication | Knowledge
Sub-Goals | [5 empty] | Sub-goals that extend from your Critical Goals will be TRACKed here. Don’t forget to link with some kind of indicator to keep your goals organized.
Time | Resources | Actions | Communication | Knowledge

## Example
Primary Goal: Build Small Deck in the Backyard | [5 empty] | Begin with your primary goal, whether it’s a project or a life-changing goal. Adding pictures is my recommendation because it provides visual appeal and helps boost motivation to keep moving forward.
Time | Resources | Actions | Communication | Knowledge
2 weeks 1-14 Feb | *Lumbar *Auger *City Public Service *John (Neighbor) *Stain and Seal | Build the back yard deck to boost home value | Ask John for help, he built his last year and increased his home value. | *Type of wood? *type of auger? *Do I need to rent an auger? |  | TRACK your primary goal first. This will allow you to identify your Critical Goals.
Critical Goals |  |  |  |  | Sub-Goal Links | Critical Goals are the non-negotiable goals. So without these goals being achieved, the project will not survive.
Time | Resources | Actions | Communication | Knowledge
2023-02-01 | City Public Service Dept | Check for utility lines underground | Call City Public Service for availability 1-800-###-#### | know plans can change if there are utility lines where we want to dig?
2023-02-02 | *Auger *Acme Tool Rental | rent auger to dig holes | Call Acme Tool Rental for availability 555-1234 | *availability of auger? *price per day or hour? | 1
2023-02-12 | Quality waterproof stain and seal | Stain and seal deck when construction complete | *ask Acme Paints which stain and seal is best for our weather | *how many gallons? *how many coats of stain and seal
Sub-Goals | [5 empty] | *Sub-goals are extended from TRACK-ing Critical Goals. Sometimes, you will come up with sub-goals based on needs that will support Critical Goals. This is where the granularity of Goal TRACK-ing comes in. *Notice how these two sub-goals are linked to one of the Critical Goals using the identifier "1". You can use anything you want such as colors, letters, or shapes. Use what helps you!
Time | Resources | Actions | Communication | Knowledge
2023-02-03 | *Auger Manual *John's expertise | *Learn how to use the auger *Dig some test holes somewhere | Let John know the date we are getting the auger | Will I need some concrete?…looks like another sub-goal coming! | 1.a
2023-02-04 | Concrete | Need to get concrete to fill holes for the stability of the deck | ask John the type and how much we need | *how much? *type of concrete? | 1.b